METRO DETROIT AIRPORT — IT CENTER

IT Center Network & Airport Operations Systems Modernization

Project Charter · Communication Plan · Training & End-User Support / Cutover Plan

| Project Type | Technology |
| --- | --- |
| Prepared By | Lisa Lewandowski, Project Manager |
| Date | Illustrative portfolio project — dated for a 9-month delivery cycle |
| Document Status | Baselined — Illustrative / Self-Directed Practice Project |

PORTFOLIO SCENARIO — This is an illustrative, self-directed practice project prepared as candidate work for an IT Project Manager role (Technology Services department). It is not a record of an actual Metro Detroit Airport engagement; it demonstrates the PM documentation standard the author would run on a comparable technology-modernization project. Companion project: “01 — Data Center & NOC Build-Out” (Construction/Infrastructure), whose facility this project fits out and migrates into.

# 1. Project Charter

## 1.1  Purpose / Business Case

The airport's core network runs on end-of-life switches and routers over a single-threaded fiber backbone connecting terminal concourses to the legacy server room — an outage risk for baggage handling, passenger processing, and security systems, and a barrier to vendor support renewal. This project modernizes the network core, migrates critical operations systems into the newly constructed IT Center data center/NOC, and upgrades monitoring and cybersecurity capability to current technical standards.

## 1.2  Objectives

- Replace end-of-life core/distribution switches and routers with a redundant, vendor-supported platform.

- Design and deploy a redundant fiber backbone linking all terminal concourses to the new data center with no single point of failure.

- Migrate baggage handling, passenger processing, and access-control/security systems into the new data center with zero unplanned downtime during cutover.

- Implement centralized network monitoring/alerting and harden cybersecurity posture (segmentation, MFA, patch compliance) to current technical standards.

- Deliver training and hypercare support so Airport Operations and airline tenant IT staff can operate and support the new environment independently.

## 1.3  Success Criteria / KPIs

- All cutover events completed within approved maintenance windows with zero unplanned outage to live airport operations.

- 100% of in-scope systems migrated and validated against acceptance test criteria.

- Mean time to detect (MTTD) network incidents improves, measured via the new monitoring platform against pre-go-live baseline.

- Final cost within approved budget +/- 5%.

- End-user support tickets tied to the new environment return to steady-state volume within 30 days of go-live (hypercare exit criteria).

## 1.4  Sponsor & Project Team

Executive Sponsor:  Director, Technology Services, Metro Detroit Airport IT Center

Project Manager:  Lisa Lewandowski

Core team: Network Engineering Lead, Cybersecurity Lead, Systems/Server Administrators, Systems Integrator (vendor), and a Help Desk/end-user support lead. Cross-functional stakeholders: Airport Operations leadership (approves cutover windows), airline tenant IT liaisons (coordinate testing on shared systems), and the network equipment OEM account team.

## 1.5  Scope

In Scope

- Core/distribution network refresh: switches, routers, and a redundant fiber backbone to the new data center.

- Migration and cutover of baggage handling, passenger processing, and access-control/security system servers into the new data center.

- Network monitoring and alerting platform implementation.

- Cybersecurity hardening: network segmentation, MFA, and firmware/patch compliance to current technical standards.

- End-user training and go-live hypercare support for Airport Operations and airline tenant IT staff.

- Vendor management for the network equipment OEM and systems integrator.

Out of Scope

- Physical construction of the data center/NOC facility (covered under the companion Data Center & NOC Build-Out project).

- Passenger-facing Wi-Fi and kiosk hardware refresh (separate initiative).

- Replacement of airline-owned systems (airline tenant responsibility; this project provides connectivity and coordination only).

## 1.6  High-Level Milestones

| Milestone | Target Date | Key Deliverable |
| --- | --- | --- |
| Requirements & Technical Design Approved | Month 1 | Design and technical-standards compliance sign-off |
| Vendor Procurement & Core Equipment Delivered | Month 2 | Purchase orders issued; equipment on-site |
| Fiber Backbone Installed & Tested | Month 4 | Redundant backbone validated (dependent on facility handover from Construction project) |
| Core Network Cutover Complete | Month 5 | All concourses live on new core network |
| Operations Systems Migration Complete | Month 7 | Baggage, passenger processing, and access-control systems migrated and validated |
| Monitoring & Cybersecurity Hardening Complete | Month 8 | Monitoring platform live; hardening checklist signed off |
| Training, Hypercare & Project Closeout | Month 9 | Training delivered; hypercare exit criteria met; closeout accepted |

## 1.7  Assumptions

- The companion Data Center & NOC Build-Out project delivers Substantial Completion of the facility before backbone/equipment installation begins.

- Cutover windows can be scheduled during low-traffic overnight periods with Airport Operations approval.

- Airline tenants can provide IT liaison availability for coordinated system testing.

- Vendor equipment lead times hold to quoted timelines once purchase orders are issued.

## 1.8  Constraints

- Cutover activities cannot cause unplanned downtime to live baggage handling, passenger processing, or security systems.

- All network and security changes must meet TSA and airport IT technical standards and pass change-control approval before implementation.

- Budget is fixed; any scope change requires an approved Change Request before work proceeds.

- Airline tenant systems are outside the project's direct control — coordination-dependent, not command-dependent.

## 1.9  Budget Summary

| Category | Amount |
| --- | --- |
| Total Approved Budget | $2,650,000 |
| Contingency Reserve | $185,000 (7%) |
| Funding Source | Airport Authority Capital Improvement Program (CIP) — Technology Services line item |

## 1.10  Approval

| Role | Name | Signature / Date |
| --- | --- | --- |
| Executive Sponsor — Director, Technology Services | [Name] | [Signature / Date] |
| Project Manager | Lisa Lewandowski | [Signature / Date] |
| Airport Operations Director | [Name] | [Signature / Date] |

# 2. Stakeholder Communication Management Plan

Communication is structured around the vendor delivery cadence, Airport Operations' cutover-approval process, and Technology Services' monthly governance. All schedule, budget, risk, and vendor status lives in the PM Tracking Workbook; the PM is the single point of contact between the project team, systems integrator/vendors, airline tenant IT liaisons, and Technology Services leadership.

| Audience | Information Needs | Method | Frequency | Owner |
| --- | --- | --- | --- | --- |
| Director, Technology Services (Sponsor) | Budget, schedule health, risk, go/no-go decisions | Monthly steering review | Monthly | PM |
| Airport Operations Leadership | Cutover window requests and approvals | Change-control meeting | Bi-weekly (weekly during cutover phase) | PM |
| Airline Tenant IT Liaisons | Coordinated testing schedule, system impacts | Coordination call / email | Bi-weekly during migration phase | PM |
| Network/Systems Vendor & Integrator | Technical design, delivery status, defect resolution | Vendor status meeting | Weekly | PM / Network Engineering Lead |
| Help Desk / End Users | Go-live dates, training schedule, support channels | Email bulletin / briefing | Per milestone | PM / Help Desk Lead |

# 3. Training & End-User Support / Cutover Plan

End-user readiness is treated as a deliverable, not an afterthought: internal engineering staff, Airport Operations, and airline tenant IT liaisons are trained and supported through a defined hypercare period before the project closes.

| Activity | Audience | Method | Timing | Owner |
| --- | --- | --- | --- | --- |
| Network Engineering platform training (new switch/router OS, monitoring tools) | Internal Network Engineering team | Vendor-led technical training | Month 3 | Network Engineering Lead |
| Cutover-window briefing | Airport Operations, Airline Tenant IT liaisons | Briefing + written runbook | Month 4–5 | PM |
| End-user quick-reference guide & Help Desk runbook handoff | Help Desk / Support staff | Documentation + walkthrough session | Month 7 | PM / Systems Integrator |
| Go-live hypercare support (extended coverage) | All end users of migrated systems | Extended Help Desk hours + on-call engineering | Month 7–8 (2 weeks post-cutover) | Help Desk Lead |
| 30-day post-go-live support review / hypercare exit | Sponsor, Airport Operations | Metrics review meeting | Month 9 | PM |