## Instructions
IT Center Network & Airport Operations Systems Modernization — PM Tracking Workbook
Metro Detroit Airport — IT Center
Metro Detroit Airport IT Center — Technology project. Illustrative, self-directed portfolio scenario (see Charter document for full context); not a record of an actual Authority engagement.
Pairs with 01_Charter_Comms_Training_Cutover_Plan.docx and 03_Status_and_Closeout_Report.docx in this folder.
Formula cells (Budget Tracker variance/%, Risk Register score, TOTAL row) recalculate automatically — do not overtype them.
Color key:
Yellow fill = example row showing expected format — replace/delete before use
Light blue fill = alternating row shading (no action needed)
Navy header row = column titles (do not edit)

## WBS_Schedule
Work Breakdown Structure & Schedule
Phase | WBS ID | Task / Deliverable | Owner | Start Date | End Date | Duration (days) | % Complete | Status | Predecessor
Design | 1.0 | Requirements gathering & technical design | Network Engineering Lead | Month 1 | Month 1 | 25 | 100% | Complete | -
Design | 1.1 | Technical standards / change-control approval | PM | Month 1 | Month 1 | 10 | 100% | Complete | 1.0
Procurement | 2.0 | Vendor procurement (switches, routers, SIEM) | PM | Month 2 | Month 2 | 20 | 100% | Complete | 1.1
Backbone Install | 3.0 | Fiber backbone install (dependent on facility handover) | Systems Integrator | Month 3 | Month 4 | 40 | 100% | Complete | 2.0
Backbone Install | 3.1 | Backbone testing & validation | Network Engineering Lead | Month 4 | Month 4 | 12 | 100% | Complete | 3.0
Core Cutover | 4.0 | Core network cutover — all concourses | Network Engineering Lead | Month 5 | Month 5 | 20 | 100% | Complete | 3.1
Systems Migration | 5.0 | Passenger processing system migration | Systems Integrator | Month 6 | Month 6 | 20 | 100% | Complete | 4.0
Systems Migration | 5.1 | Baggage handling system migration | Systems Integrator | Month 6 | Month 7 | 25 | 85% | In Progress | 4.0
Systems Migration | 5.2 | Access-control/security system migration | Systems Integrator | Month 7 | Month 7 | 15 | 0% | Not Started | 5.1
Monitoring & Hardening | 6.0 | Monitoring/SIEM platform go-live | Cybersecurity Lead | Month 7 | Month 8 | 20 | 40% | In Progress | 5.2
Monitoring & Hardening | 6.1 | Cybersecurity hardening checklist | Cybersecurity Lead | Month 8 | Month 8 | 15 | 0% | Not Started | 6.0
Training & Closeout | 7.0 | Training, hypercare & project closeout | PM | Month 9 | Month 9 | 20 | 0% | Not Started | 6.1

## Budget_Tracker
Budget Tracker
Cost Category | Budgeted ($) | Committed ($) | Actual to Date ($) | Variance ($) | % Used | Notes
Network Hardware (switches/routers) | 980000 | 970000 | 965000 | -15000 | 98.47% | Complete
Fiber/Cabling Installation | 310000 | 300000 | 298000 | -12000 | 96.13% | Complete
Systems Migration (Integrator Labor) | 540000 | 420000 | 385000 | -155000 | 71.3% | On track
Monitoring / SIEM Platform | 260000 | 268000 | 268000 | 8000 | 103.1% | Change Request #2 — added log-source licensing, +$8,000
Cybersecurity Hardening | 150000 | 40000 | 20000 | -130000 | 13.33% | In progress
Training & Documentation | 90000 | 0 | 0 | -90000 | 0% | Not started
Vendor Support / Warranty (Yr 1) | 135000 | 135000 | 135000 | 0 | 100% | Complete
Contingency | 185000 | 8000 | 8000 | -177000 | 4.324% | 1 approved Change Request — SIEM licensing
TOTAL | 2650000 | 2141000 | 2079000 | -571000 | 78.45%

## RACI_Matrix
RACI Matrix (R = Responsible · A = Accountable · C = Consulted · I = Informed)
Task / Deliverable | PM | Sponsor (Tech Services) | Network Eng Lead | Cybersecurity Lead | Systems Integrator | Airport Ops | Airline Tenant IT
Technical design approval | A | A | R | C | C | I | I
Vendor procurement | R | A | C | I | I | I | I
Backbone install & test | A | I | R | I | R | C | I
Core network cutover | A | I | R | C | R | A | C
Operations systems migration | A | I | C | C | R | A | C
Monitoring & cybersecurity hardening | A | I | C | R | C | I | I
Training & hypercare | R | I | C | I | C | A | C
Go-live / closeout sign-off | R | A | C | C | C | A | I

## Stakeholder_Register
Stakeholder Register
Name / Role | Organization | Interest | Influence (H/M/L) | Engagement Strategy | Contact
Director, Technology Services | Metro Detroit Airport IT Center | Executive sponsor; budget owner | H | Monthly steering review; escalation contact | [email/phone]
Network Engineering Lead | Metro Detroit Airport IT Center | Owns technical design & cutover execution | H | Weekly working session | [email/phone]
Cybersecurity Lead | Metro Detroit Airport IT Center | Owns hardening standards & sign-off | H | Bi-weekly review; hardening checklist owner | [email/phone]
Airport Operations Director | Metro Detroit Airport | Approves cutover windows; receiving owner | H | Change-control meeting; go/no-go authority | [email/phone]
Airline Tenant IT Liaisons (multiple) | Airline tenants | Coordinate shared-system testing | M | Bi-weekly coordination calls during migration | [email/phone]
Systems Integrator Project Manager | Integrator firm | Delivers migration & cutover work | H | Weekly vendor status meeting | [email/phone]
Help Desk Manager | Metro Detroit Airport IT Center | Owns end-user support & hypercare | M | Training handoff; hypercare metrics review | [email/phone]

## Risk_Register
Risk Register
Risk ID | Description | Category | Probability (1-5) | Impact (1-5) | Score | Response Strategy | Owner | Status
R1 | Cutover causes unplanned outage to live operations systems | Operational | 2 | 5 | 10 | Overnight low-traffic windows; rollback plan rehearsed pre-cutover | PM / Network Eng Lead | Closed (cutover complete)
R2 | Vendor equipment delivery delayed post-PO | Procurement | 2 | 4 | 8 | PO issued with confirmed lead times; weekly vendor status check | PM | Closed
R3 | Airline tenant testing availability conflicts compress migration window | Coordination | 3 | 2 | 6 | Build float into migration schedule; confirm liaison availability early | PM | Monitoring
R4 | Cybersecurity hardening review surfaces additional licensing/scope needs | Technical | 3 | 3 | 9 | Change Request process; fund from contingency if approved | Cybersecurity Lead | Open
R5 | Post-go-live ticket spike from training gaps | Adoption | 3 | 3 | 9 | Hypercare staffing plan sized per migrated system; 30-day exit review | Help Desk Manager | Monitoring
R6 | Data migration integrity issue (records lost/corrupted in transfer) | Technical | 2 | 5 | 10 | Full backup before each migration event; acceptance test sign-off before decommissioning legacy system | Systems Integrator | Monitoring

## Issue_Change_Log
Issue & Change Log
ID | Type (Issue/Change) | Description | Date Raised | Owner | Priority | Status | Resolution / Decision
I3 | Issue | Airline tenant requested a later testing slot, compressing migration window | Month 6 | PM | Low | Resolved | Rescheduled within existing float; no baseline impact
C2 | Change | Additional SIEM log-source licensing required after hardening review | Month 6 | Cybersecurity Lead | Medium | Approved | Change Request #2 executed, +$8,000, funded from contingency

## Vendor_Contractor_Register
Vendor / Contractor Register
Vendor / Contractor | Scope of Work | Contract Value ($) | Start Date | End Date | Performance Rating | Key Contact
[Network Equipment OEM] | Core/distribution switches, routers, licensing | 980000 | Month 2 | Month 5 | Meets expectations | [Contact name / email]
[Systems Integrator firm] | Fiber install, systems migration, cutover execution | 850000 | Month 3 | Month 8 | Meets expectations | [Contact name / email]
[SIEM/Monitoring platform vendor] | Monitoring platform license & implementation support | 268000 | Month 6 | Month 8 | Meets expectations | [Contact name / email]
[Fiber/Cabling contractor] | Backbone cable install & termination | 300000 | Month 3 | Month 4 | Meets expectations | [Contact name / email]