METRO DETROIT AIRPORT — IT CENTER

IT Center Network & Airport Operations Systems Modernization — Status Report

Recurring Status Report — Illustrative Snapshot (Month 6 of 9)

PORTFOLIO SCENARIO — illustrative status and closeout snapshots for a self-directed practice project (see Charter for context).

| Reporting Period | Month 6 of 9 (Operations Systems Migration phase) |
| --- | --- |
| Overall Project Status | Green |
| Schedule Status | Green — on baseline |
| Budget Status | Yellow — SIEM licensing scope addition tracked as Change Request |
| Prepared By | Lisa Lewandowski, Project Manager |

## Accomplishments This Period

- Core network cutover completed for all terminal concourses with zero unplanned downtime.

- Redundant fiber backbone tested and validated at full design capacity.

- Passenger processing system migration completed and passed acceptance testing.

- Baggage handling system migration testing underway; two of three system components cut over successfully.

## Planned Next Period

- Complete final baggage-handling component cutover during next approved maintenance window.

- Begin access-control/security system migration.

- Finalize SIEM platform licensing scope with vendor following Change Request approval.

- Schedule Help Desk runbook handoff session with Systems Integrator.

## Budget Snapshot

| Category | Budgeted | Actual to Date | Variance | % Used |
| --- | --- | --- | --- | --- |
| Network Hardware (switches/routers) | $980,000 | $965,000 | -$15,000 | 98% |
| Fiber/Cabling Installation | $310,000 | $298,000 | -$12,000 | 96% |
| Systems Migration (Integrator Labor) | $540,000 | $385,000 | -$155,000 | 71% |
| Monitoring / SIEM Platform | $260,000 | $268,000 | +$8,000 | 103% |

## Top Risks & Issues

| ID | Description | Impact | Mitigation / Next Step | Owner |
| --- | --- | --- | --- | --- |
| R4 | Cybersecurity hardening review flagged additional SIEM log-source licensing needed | Medium | Change Request submitted; funding from contingency under review | Cybersecurity Lead / PM |
| I3 | One airline tenant requested a later testing slot, compressing the migration window | Low | Rescheduled within existing float; no baseline impact | PM |

## Decisions Needed / Escalations

- Sponsor approval requested for Change Request #2 (SIEM log-source licensing, +$8,000) funded from contingency — decision needed before Month 7 hardening milestone.

METRO DETROIT AIRPORT — IT CENTER

IT Center Network & Airport Operations Systems Modernization — Project Closeout Report

Final Closeout Report — Illustrative Snapshot

## Final Summary vs. Baseline

| Dimension | Baseline | Final (Actual) | Variance |
| --- | --- | --- | --- |
| Schedule | Month 9 closeout | Month 9 (on baseline) | On time |
| Budget | $2,650,000 | $2,611,400 | -$38,600 (1.5% under budget) |
| Scope | Network refresh + systems migration + monitoring/security hardening + training | Delivered as baselined; one approved Change Request (SIEM licensing, +$8,000) | 1 Change Request, within contingency |

## Deliverables Accepted

| Deliverable | Accepted By | Date | Notes |
| --- | --- | --- | --- |
| Core network cutover (all concourses) | Airport Operations Director | Month 5 | Zero unplanned downtime |
| Operations systems migration (baggage, passenger processing, access control) | Technology Services Director | Month 7 | All acceptance tests passed |
| Monitoring platform & cybersecurity hardening sign-off | Cybersecurity Lead | Month 8 | Hardening checklist 100% complete |
| Training materials & hypercare exit report | Help Desk Manager | Month 9 | Ticket volume returned to steady-state on day 24 of hypercare |

## Lessons Learned — What Went Well

- Scheduling cutovers in coordination with Airport Operations' event calendar, rather than a fixed date, avoided every high-traffic conflict.

- Bringing the Systems Integrator into technical design early reduced rework during the migration phase.

- A written cutover runbook shared with airline tenant IT liaisons in advance kept coordination issues to scheduling only, not technical surprises.

## Lessons Learned — What Could Improve

- Cybersecurity hardening requirements (SIEM log sources) should have been scoped against the full system inventory during Technical Design, not discovered during hardening.

- Hypercare staffing was sized for baggage/passenger systems; access-control ticket volume ran slightly higher than planned in week one.

## Recommendations for Future Projects

- For future migrations, include a full log-source inventory pass as a Technical Design deliverable, not a hardening-phase task.

- Size hypercare Help Desk coverage per migrated system independently, rather than as a single blended estimate.

## Outstanding Items / Transition to Operations

- Monitor SIEM licensing Change Request cost against contingency through the 90-day warranty window — owner: PM.

- Airline tenant IT liaisons to complete their own internal sign-off on shared-system connectivity — owner: Airline tenant IT (tracked, not owned, by PM).

## Sign-Off

| Role | Name | Signature / Date |
| --- | --- | --- |
| Executive Sponsor — Director, Technology Services | [Name] | [Signature / Date] |
| Project Manager | Lisa Lewandowski | [Signature / Date] |
| Airport Operations Director | [Name] | [Signature / Date] |