## Instructions
IT Center Data Center & NOC Build-Out — PM Tracking Workbook
Metro Detroit Airport — IT Center
Metro Detroit Airport IT Center — Construction/Infrastructure project. Illustrative, self-directed portfolio scenario (see Charter document for full context); not a record of an actual Authority engagement.
Pairs with 01_Charter_Comms_Commissioning_Plan.docx and 03_Status_and_Closeout_Report.docx in this folder.
Formula cells (Budget Tracker variance/%, Risk Register score, TOTAL row) recalculate automatically — do not overtype them.
Color key:
Yellow fill = example row showing expected format — replace/delete before use
Light blue fill = alternating row shading (no action needed)
Navy header row = column titles (do not edit)

## WBS_Schedule
Work Breakdown Structure & Schedule
Phase | WBS ID | Task / Deliverable | Owner | Start Date | End Date | Duration (days) | % Complete | Status | Predecessor
Design & Permitting | 1.0 | Schematic & design development | MEP Engineer of Record | Month 1 | Month 3 | 60 | 100% | Complete | -
Design & Permitting | 1.1 | Permit submission & AHJ approval | PM | Month 2 | Month 3 | 30 | 100% | Complete | 1.0
Sitework & Foundation | 2.0 | Sitework, excavation, foundation pour | General Contractor | Month 3 | Month 5 | 55 | 100% | Complete | 1.1
Structural & Shell | 3.0 | Structural steel, envelope, roof dry-in | General Contractor | Month 5 | Month 7 | 55 | 100% | Complete | 2.0
MEP Rough-In | 4.0 | Electrical rough-in (power, UPS, generator) | Electrical Subcontractor | Month 7 | Month 9 | 60 | 80% | In Progress | 3.0
MEP Rough-In | 4.1 | Mechanical rough-in (cooling, containment) | Mechanical Subcontractor | Month 7 | Month 9 | 60 | 65% | In Progress | 3.0
MEP Rough-In | 4.2 | Fire suppression rough-in | Fire Protection Subcontractor | Month 8 | Month 9 | 30 | 90% | In Progress | 3.0
Finishes & Security | 5.0 | Raised floor, cable tray, finishes | General Contractor | Month 9 | Month 11 | 60 | 0% | Not Started | 4.0
Finishes & Security | 5.1 | Badge access, mantrap, CCTV install | Security Systems Integrator | Month 10 | Month 11 | 30 | 0% | Not Started | 5.0
Commissioning | 6.0 | Level 1-2 Cx (startup, functional test) | Commissioning Agent | Month 12 | Month 13 | 30 | 0% | Not Started | 5.1
Commissioning | 6.1 | Level 3-4 Cx (integrated systems test) | Commissioning Agent | Month 13 | Month 13 | 15 | 0% | Not Started | 6.0
Handover | 7.0 | O&M training, as-built turnover, Substantial Completion | PM | Month 14 | Month 14 | 15 | 0% | Not Started | 6.1

## Budget_Tracker
Budget Tracker
Cost Category | Budgeted ($) | Committed ($) | Actual to Date ($) | Variance ($) | % Used | Notes
Sitework & Foundation | 650000 | 650000 | 645000 | -5000 | 99.23% | Complete
Structural / Shell | 850000 | 850000 | 838000 | -12000 | 98.59% | Complete
Electrical (Power/UPS/Generator) | 1000000 | 903000 | 810000 | -190000 | 81% | Switchgear lead time being absorbed via schedule compression
Mechanical (Cooling) | 780000 | 573000 | 507000 | -273000 | 65% | On track
Fire Suppression | 170000 | 166000 | 160000 | -10000 | 94.12% | Complete
Raised Floor & Finishes | 210000 | 0 | 0 | -210000 | 0% | Not started
Security Systems | 150000 | 0 | 0 | -150000 | 0% | Not started
Permits & Fees | 50000 | 50000 | 48000 | -2000 | 96% | Complete
Commissioning | 50000 | 0 | 0 | -50000 | 0% | Not started
Contingency | 340000 | 61000 | 61000 | -279000 | 17.94% | 1 approved Change Order — egress lighting, $18,200
TOTAL | 4250000 | 3253000 | 3069000 | -1181000 | 72.21%

## RACI_Matrix
RACI Matrix (R = Responsible · A = Accountable · C = Consulted · I = Informed)
Task / Deliverable | PM | Facilities Sponsor | General Contractor | MEP Engineer | IT Ops (Receiving) | Security/Badging
Design Development approval | A | A | C | R | C | I
Permitting & AHJ submission | A | I | R | C | I | I
Sitework / foundation / shell | A | I | R | C | I | I
MEP rough-in | A | I | R | R | C | I
Badge access / security systems install | A | C | C | I | C | R
Commissioning (Levels 1-4) | A | I | C | R | C | I
Substantial Completion sign-off | R | A | C | C | A | I

## Stakeholder_Register
Stakeholder Register
Name / Role | Organization | Interest | Influence (H/M/L) | Engagement Strategy | Contact
Director, Facilities & Infrastructure | Metro Detroit Airport IT Center | Executive sponsor; capital budget owner | H | Monthly steering review; escalation contact | [email/phone]
IT Center Operations Manager | Metro Detroit Airport IT Center | Receiving owner; will operate the facility | H | Bi-weekly coordination; leads commissioning witness | [email/phone]
General Contractor Project Manager | GC firm | Delivers construction on schedule/budget | H | Weekly site meeting; RFI/submittal log | [email/phone]
MEP Engineer of Record | Engineering firm | Design authority for power/cooling/fire systems | M | Design reviews; rough-in inspections | [email/phone]
Airport Security / Badging Office | Metro Detroit Airport | Controls contractor site access | M | Advance badge-request coordination | [email/phone]
Local Building Department (AHJ) | Municipal government | Permit approval and inspections | M | Formal inspection requests; code walkthroughs | [email/phone]
Airport Authority Capital Committee | Metro Detroit Airport IT Center | Approves capital funding, monitors GMP | H | Monthly capital program report | [email/phone]

## Risk_Register
Risk Register
Risk ID | Description | Category | Probability (1-5) | Impact (1-5) | Score | Response Strategy | Owner | Status
R1 | Utility feeder capacity insufficient for dual-feed design | Technical/Utility | 2 | 5 | 10 | Confirm capacity at Design Development; secure utility commitment letter before GMP lock | PM / MEP Engineer | Closed
R2 | Long-lead equipment (generator, UPS, chillers) delayed | Procurement | 3 | 4 | 12 | Order at Notice to Proceed; track supplier milestones monthly | PM | Monitoring
R3 | Medium-voltage switchgear lead time extends 4+ weeks | Procurement | 4 | 4 | 16 | Expedite fee approved; resequence rough-in to protect Cx start | PM / MEP Engineer | Open
R4 | Weather delays to sitework/foundation | Environmental | 3 | 3 | 9 | Schedule float built into sitework phase; monitor forecast weekly | General Contractor | Closed
R5 | Unforeseen underground utilities/soil conditions | Site | 2 | 4 | 8 | Geotechnical survey completed pre-GMP; contingency reserved | General Contractor | Closed
R6 | AHJ inspection delays or repeat re-inspections | Regulatory | 3 | 3 | 9 | Pre-submission code walkthrough with AHJ at 60% design | PM | Monitoring
R7 | Contractor badge/security clearance delays site access | Security | 2 | 3 | 6 | Submit badge requests 3 weeks ahead of trade mobilization | PM / Security Liaison | Monitoring

## Issue_Change_Log
Issue & Change Log
ID | Type (Issue/Change) | Description | Date Raised | Owner | Priority | Status | Resolution / Decision
I1 | Issue | Switchgear supplier confirmed 4-week lead-time extension | Month 8 | PM | High | Open | Schedule compression plan approved; weekend shift added at GC cost within contingency
I2 | Issue | AHJ requested additional egress-lighting detail before rough-in sign-off | Month 9 | General Contractor | Medium | Resolved | Revised detail submitted and approved; re-inspection passed
C1 | Change | Add emergency egress lighting circuit not in original electrical design | Month 9 | MEP Engineer | Medium | Approved | Change Order #1 executed, $18,200, funded from contingency

## Vendor_Contractor_Register
Vendor / Contractor Register
Vendor / Contractor | Scope of Work | Contract Value ($) | Start Date | End Date | Performance Rating | Key Contact
[General Contractor firm] | Design-build GC services; site supervision | 2450000 | Month 1 | Month 14 | Meets expectations | [Contact name / email]
[Electrical Subcontractor] | Power distribution, UPS, generator install | 1450000 | Month 6 | Month 10 | Meets expectations | [Contact name / email]
[Mechanical Subcontractor] | Precision cooling, chillers, containment | 980000 | Month 6 | Month 10 | Meets expectations | [Contact name / email]
[Security Systems Integrator] | Badge access, mantrap, CCTV, monitoring | 190000 | Month 10 | Month 11 | Not yet rated | [Contact name / email]
[Commissioning Agent firm] | Level 1-4 commissioning oversight | 130000 | Month 1 | Month 14 | Meets expectations | [Contact name / email]
[Generator/UPS equipment vendor] | Long-lead equipment supply | 890000 | Month 2 | Month 12 | Watch — lead-time slip | [Contact name / email]