METRO DETROIT AIRPORT — IT CENTER

IT Center Data Center & NOC Build-Out — Status Report

Recurring Status Report — Illustrative Snapshot (Month 9 of 14)

PORTFOLIO SCENARIO — illustrative status and closeout snapshots for a self-directed practice project (see Charter for context).

| Reporting Period | Month 9 of 14 (MEP Rough-In phase) |
| --- | --- |
| Overall Project Status | Yellow |
| Schedule Status | Yellow — 6 business days behind due to switchgear lead time |
| Budget Status | Green — 2% under committed forecast |
| Prepared By | Lisa Lewandowski, Project Manager |

## Accomplishments This Period

- Structural shell and building dry-in completed and passed envelope inspection.

- Electrical rough-in 80% complete; generator pad poured and dual utility feed conduit run confirmed by the utility company.

- Mechanical rough-in (chiller piping, CRAH duct) 65% complete.

- Fire suppression pre-action system rough-in passed first-round AHJ inspection.

## Planned Next Period

- Complete electrical rough-in and schedule switchgear energization inspection.

- Finish mechanical rough-in and begin raised-floor substrate installation.

- Submit Level 1 commissioning plan to the Commissioning Agent for review.

- Confirm badge-access provisioning list for finishes-phase subcontractors with Airport Security.

## Budget Snapshot

| Category | Budgeted | Actual to Date | Variance | % Used |
| --- | --- | --- | --- | --- |
| Electrical (Power/UPS/Generator) | $1,000,000 | $810,000 | -$190,000 | 81% |
| Mechanical (Cooling) | $780,000 | $507,000 | -$273,000 | 65% |
| Structural / Shell / Sitework | $1,500,000 | $1,483,000 | -$17,000 | 99% |
| Contingency Remaining | $340,000 | $61,000 used | $279,000 remaining | 18% |

## Top Risks & Issues

| ID | Description | Impact | Mitigation / Next Step | Owner |
| --- | --- | --- | --- | --- |
| R3 | Medium-voltage switchgear lead time extended by supplier 4 weeks | High | Expedite fee approved; resequencing rough-in tasks to protect Cx start | PM / MEP Engineer |
| I2 | AHJ requested additional egress-lighting detail before final rough-in sign-off | Medium | Revised detail submitted; re-inspection scheduled next week | GC |

## Decisions Needed / Escalations

- Sponsor approval requested to absorb the 4-week switchgear delay via schedule compression (added weekend shift, GC cost within contingency) rather than pushing Substantial Completion — decision needed within 5 business days.

METRO DETROIT AIRPORT — IT CENTER

IT Center Data Center & NOC Build-Out — Project Closeout Report

Final Closeout Report — Illustrative Snapshot

## Final Summary vs. Baseline

| Dimension | Baseline | Final (Actual) | Variance |
| --- | --- | --- | --- |
| Schedule | Month 14 Substantial Completion | Month 14 + 6 business days | +6 business days (switchgear lead time; recovered via compression) |
| Budget | $4,250,000 GMP | $4,168,400 | -$81,600 (1.9% under GMP) |
| Scope | 9,000 sq. ft. data center/NOC shell + N+1 MEP + security rough-in | Delivered as baselined; one approved Change Order for added egress lighting | 1 Change Order, $18,200 (within contingency) |

## Deliverables Accepted

| Deliverable | Accepted By | Date | Notes |
| --- | --- | --- | --- |
| Certificate of Occupancy | Local Building Department (AHJ) | Month 14 | Issued on first re-inspection |
| Level 1–4 Commissioning Report | IT Center Operations Manager | Month 14 | All checklist items passed; two minor punch items closed same week |
| As-Built Drawings & O&M Manuals | IT Center Operations Manager | Month 14 | Delivered in hard copy and shared document repository |

## Lessons Learned — What Went Well

- Ordering long-lead electrical/mechanical equipment at Notice to Proceed absorbed most supply-chain risk before it could hit the critical path.

- Weekly GC site meetings with a standing RFI/submittal log kept design clarifications from stalling rough-in work.

- Early, direct coordination with Airport Security on contractor badging avoided access delays during the finishes phase.

## Lessons Learned — What Could Improve

- Switchgear lead time should have been reconfirmed with the supplier at the 60%-design milestone, not only at order placement.

- AHJ egress-lighting requirements surfaced late; a pre-submission code walkthrough with the AHJ earlier in Design Development would have caught this.

## Recommendations for Future Projects

- For future data-center builds, add a supplier lead-time reconfirmation checkpoint at each design milestone for all long-lead MEP equipment.

- Schedule an informal AHJ pre-review at 60% design for any project with life-safety systems (egress, fire suppression) to reduce re-inspection cycles.

## Outstanding Items / Transition to Operations

- Two minor punch-list items (door hardware adjustment, label plate reorder) — owner: GC, due within 30 days of handover.

- Transition of the facility to the companion Network & Systems Modernization project for technology fit-out — owner: PM, kickoff scheduled next reporting period.

## Sign-Off

| Role | Name | Signature / Date |
| --- | --- | --- |
| Executive Sponsor — Director, Facilities & Infrastructure | [Name] | [Signature / Date] |
| Project Manager | Lisa Lewandowski | [Signature / Date] |
| IT Center Operations Manager (Receiving Owner) | [Name] | [Signature / Date] |