## Slide 1
LEAN SIX SIGMA BLACK BELT PROJECT
Optimizing Lab Operations
Through Lean Six Sigma Application
Lisa Lewandowski | Q2 2024 | TriCore Reference Laboratories | Siena Heights University PDC
Blackbelt Validation Project — Case Study

## Slide 2
PROJECT RESULTS AT A GLANCE
$894K+
Minimum Annual
Revenue Recovery
31%
Throughput
Gap Closed
2.6 → 2.9
Sigma Level
Improvement
3 Labs
Pilot Labs Tested
& Validated
TriCore Reference Laboratories · 12 Labs Across New Mexico · DMAIC Methodology

## Slide 3
DEFINE · The Challenge
Problem Statement
TriCore Medical Laboratories conducted 141,708 blood draws per year across 12 labs — but peak performance showed potential for 188,928. Daily throughput ranged from as low as 33 draws to 54 at top performance, a 21-draw daily variance.
This gap cost $400–$1,050 per lab per day, compounded overtime hours, and risked loss of federal Hill Burton Act funding.
141,708
Actual draws/year
188,928
Peak potential/year
$5–6M
Cost of Poor Quality (COPQ)
COPQ exceeds Hill Burton Act risk threshold

## Slide 4
CLIENT CONTEXT · TriCore Reference Laboratories
About TriCore
Founded 1998, headquartered in Albuquerque, NM
Non-profit entity, ~$1.5B revenue
2,200+ employees across New Mexico
Largest medical laboratory in New Mexico
Formed by merger of Presbyterian Healthcare, UNM Health Sciences, and The Reference Laboratory
Project scope: 12 Reference Lab locations, blood draw operations only
Why Performance Matters
Hill Burton Act federal funding at risk ($5–8M/year)
Malpractice exposure ($50K minimum per case)
Stat and overtime costs at 6% of operational budget
Delayed hospital throughput: 2–4% fewer patients served
Patient length-of-stay cost: $1,100/unbilled day
Lab 5 outperformed other 11 labs — root cause unknown

## Slide 5
DMAIC METHODOLOGY · Operational Blueprint
DEFINE
Organization history & interviews
Voice of Customer (CTS)
Problem statement
Project charter
COPQ analysis
Goal and timing
MEASURE
Baseline data collection
Current Sigma level
Gage R&R
Signal-to-noise ratio
First-time yield
Spec/unit of measure
ANALYZE
C&E matrix
FMEA
Null hypothesis
Statistical tools (T-Test)
Brainstorming
Xs of interest
IMPROVE
Pilot new approach
Conduct training
T-test experiments
Revise policy
Set new SWI
Set new UCL/LCL
CONTROL
New process baseline
Visual management
5S implementation
Control plan
Next project scope
Stretch goal tracking
Methodology driven by physician, hospital, lab, phlebotomist, and patient needs — led by senior management (Mr. Antonis, Director of Laboratory Services)

## Slide 6
MEASURE & ANALYZE · Root Cause Discovery
4 Lab Process Types Identified
A
Type A
Tech A draws / Tech B processes (sequential hand-off)
B
Type B
A & B both draw and process simultaneously (two lanes)
C
Type C
A & B draw, then process together toward end of shift
D
Type D ★ (Best)
A & B draw, process at end of shift WITH receptionist support on Type 3 (Lab 5 — best performer)
Key Findings from Process Maps & Lean Analysis
Receptionist over-processing: manual check-in vs. kiosk or lab tech triage
Broken draw/process split adds wait time vs. parallel two-lane flow
No batching creates repeated over-processing across all labs
Receptionists NOT assisting with Type 3 labels — Lab 5 does this
Missing lower spec limit — no accountability for minimum performance
Non-standard methods across labs drive inter-lab variance of 199–328 draws/week
Lean waste: Transport, Wait Time, Over-processing, Defects all present

## Slide 7
ANALYZE · Statistical Approach & Hypothesis
Null Hypothesis (H₀)
Any changes from adopting the Lab 5 process — receptionist support, two-lane workflow, and batch processing — will NOT be statistically significant.
Statistical Tool Selected
Two-Sample T-Test
Compares means of pre- and post-treatment performance in the same set of 30 randomly sampled labs. Selected over ANOVA and regression for its precision with paired pilot experiment design.
Pilot Test Design
Labs 4, 8 & 9 selected as pilot sites
30 random samples each: current process vs. Lab 5 process applied. Two days of training, four field observation days (Weeks 1 and 2). Minitab used for all statistical analysis.
Success Criteria
95% Confidence Interval
P-value < 0.05
Statistical Power validated
Results must extrapolate across all 11 underperforming labs before company-wide rollout is authorized.

## Slide 8
IMPROVE · Pilot Experiment Results
Null Hypothesis REJECTED — All 3 pilot labs achieved statistically significant improvement at 95% confidence
Lab 4
BEFORE
30.6 min
mean processing time
↓
AFTER
21.1 min
31% faster
Lab 8
BEFORE
27.8 min
mean processing time
↓
AFTER
20.9 min
25% faster
Lab 9
BEFORE
30.6 min
mean processing time
↓
AFTER
21.1 min
31% faster

## Slide 9
FINANCIAL & OPERATIONAL IMPACT
Chart: 
| Current | Goal (1,100/lab min) | Stretch (Lab 5 avg) | Max Theoretical
Annual Blood Draws | 141708 | 159876 | 172800 | 179136
+17,892
Additional draws/year
at all 12 labs (goal)
$894,600
Minimum revenue
gain per year
2.6 → 2.9
Sigma improvement
(Stretch: 3.2)
$50/draw revenue basis · 288 operating days/year/lab · 12 laboratories

## Slide 10
CONTROL · Sustaining the Improvement
Standardized Work Instructions (SWI)
Documented Lab 5 process as enterprise standard for all 12 labs
Receptionist duties redefined to include Type 3 label support
Steps followed consistently — materials stored identically across sites
Employee handbook updated with new hiring requirements
5S & Visual Management
Workstations labeled and organized per new standard
KPI indicators visible at each station
Performance data posted and updated daily
Standardized job aids for each role
Next Steps & Stretch Goals
Automate back office processing
Centralize scheduling (Phase 2 project)
Install kiosks; migrate receptionists to phlebotomist roles
Add Quality Officer for field coaching and metric oversight
Stretch target: Lab 5 weekly high of 328 draws as new standard

## Slide 11
LESSONS LEARNED · Running the Engagement
What Went Well
Director-level sponsorship (Mr. Antonis) from day one kept a 4-week, 12-lab engagement on schedule
Pairing 180+ field observations with direct interviews surfaced the Lab 5 outlier pattern faster than data alone
Validating the process change on 3 pilot labs with a two-sample T-test gave leadership a statistically defensible go/no-go
Findings presented directly to the Director of Laboratory Services kept executive sponsorship engaged through rollout
Key Takeaways
Pilot-before-scale is worth defaulting to on any multi-site rollout, not only when time allows
Frontline interviews belong in Define, not as a supplement added after baseline data collection
A sustainment plan is only as strong as the adherence check built into its charter
Statistical validation turns a process recommendation into a leadership decision, not just an analyst's opinion
Carried Into Future Engagements
Build a 30/60/90-day adherence checkpoint into every Control plan charter up front
Default to a reference-site pilot before any enterprise-wide standard-work rollout
Pair quantitative baseline data with frontline interviews from the start, not sequentially
Treat statistical validation as a standard deliverable for any before/after process claim
Keep executive sponsorship visible through implementation, not just at kickoff

## Slide 12
MY ROLE & SKILLS DEMONSTRATED
Lisa Lewandowski — LSSBB Practitioner & Process Improvement Leader
This was a real client engagement — actual data, real operations, validated conclusions. The same tools and methods applied here are what I bring to your organization.
My Contributions
Applied full DMAIC methodology across all five phases — Define through Control
Collected 180+ data points across 12 labs over 12 field observation days
Participated in 3-lab pilot experiment using two-sample T-test (95% CI)
Conducted root cause analysis: C&E matrix, FMEA, process mapping, Lean waste review
Contributed to findings presentation to Director of Laboratory Services
Supported SWI and employee handbook development for company-wide rollout
Skills Applied
Project Management: Charter, milestone planning, stakeholder management
Lean Six Sigma: DMAIC, SWI, 5S, VSM, C&E, FMEA, Gage R&R
Statistical Analysis: Two-sample T-test, Minitab, hypothesis testing, confidence intervals
Process Improvement: NVA analysis, swim lane mapping, waste elimination
Change Management: Training, SOP development, company-wide rollout
4-Week Client Engagement · Siena Heights University PDC · MBB Senseis: Dr. Ben Benson & Mr. Phil White · Q2 2024